## WASH Response_Weekly_Chaya
Disaster Response Matrix - 2025
SN | AGENY NAME | PROVINCE | DISTRICT | Name of affected Municipalities | Name OR Ward number affected | Result statement | Performance indicator/s |  |  | Target | Cumulative Progress against Target | Activities Undertaken to Achieve This Progress
Unit
TOTAL
1 | UNICEF | Bagmati |  |  |  | CCC W1: Lead and Coordination Effective leadership and coordination are established and functional | # of cluster coordination conducted at district and palikas |  | # of meetings
[7 empty] | # field mission mobilized for need and damage assessment |  | # of visits
2 | UNICEF | Bagmati |  |  |  | CCC W2. Water Supply Affected populations have safe and equitable access to, and use a sufficient quantity and quality of water to meet their drinking and domestic needs | # of people accessing a sufficient quantity and quality of water for drinking and domestic needs | Installation of HDPE tanks (5000 Ltr) in affected 6 wards for water storage including plumbing requirements at holding centers* or community settings including host communities | # of people
[8 empty] | 30 days water trucking (60,000 lit per day) for drinking and cooking only | # of people served
[8 empty] | Pipes and fittings including mobilization of locally available plumbers and technicians for quick fixes to restore the existing water supply system include the installation of mobile water treatment | # of schemes
[7 empty] | # of Water quality monitoring conducted in every ward | Moblilize technicians and trained volunteers for conducting water quality test | # of events
[8 empty] | Provide assistance for distributing WASH supplies at holding centers* and critical community settings | # of families
[8 empty] | Facilitatate Water-quality testing and monitoring | # of tests done
3 | UNICEF | Bagmati |  |  |  | CCC W3: Sanitation Affected populations have safe access to, and use appropriate sanitation facilities; and excreta is safely managed | # of people accessing appropriate sanitation services | New installation and repair & maintenance of partially damaged Latrines, bathing spaces in Communities, Camps, holding centers*, schools and health care facilities | # of people
[8 empty] | Provision of covered wastebins at HH level | # of Families
[8 empty] | Disinfectant solutions and sprayers for fumigating open defecation and waste stored points | # of events
[8 empty] | Decommissioning of tempory latrines and bathing shelter installed during response | # of latrines
[7 empty] | # of women and girls accessing menstrual hygiene management services | # of women and girls accessing menstrual hygiene management services | # of people
4 | UNICEF | Bagmati |  |  |  | CCC W4: WASH in health care facilities and learning environments/schools Affected populations have safe access to, and use, appropriate WASH services in health care and learning facilities/schools for children | # of children using safe and appropriate WASH facilities and hygiene services in learning facilities and safe spaces | Conduct hygiene promotion campaign for children in schools, camps & TLCs | # of children
[8 empty] | Provide technical and financial assistance to ensure safe, accessible and functional water supply in health care facilities, TLCs, C/WFS and Schools | # of children benefited
[8 empty] | Install temporary latrines in schools, TLCs, C/WFS and HCFs with the provision of handwashing facilities | # of latrines
5 | UNICEF | Bagmati |  |  |  | CCC W6. Hygiene promotion and community engagement for behaviour and social change At-risk and affected populations have timely access to culturally appropriate, gender- and age-sensitive information, services and interventions related to hygiene promotion, and adopt safe hygiene practices | # people reached with hygiene promotion including hand hygiene sessions (SBC internvention incorporated) | Conduct door to door campaign or mass facilitation through SBC interventions and disimmination of IEC materials for safe hygiene practices for affected populations living in communities, camp setting and holding centers | # of people
[7 empty] | # of community feedback and accountability mechanisms at holding or community centers | Conduction of interpersonal hygiene session with affected populations in camps, particulary to children lactating mothers, pregnant women and aged people | # of CFM
[7 empty] | # of people reached with critical WASH supplies (SBC internvention incorporated) | Develop, distribute and dissemination of IEC materials and media mobilization for messaging on preventive measures against outbreaks | # of people reached

## WASH Response_Daily_Chaya
Disaster Response Matrix - 2025
SN | AGENY NAME | PROVINCE | DISTRICT | Name of affected Municipalities | Name OR Ward number affected | Result statement | Performance indicator/s |  | Target | Cumulative Progress against Target | Activities Undertaken to Achieve This Progress
Unit
TOTAL
1 | UNICEF | Bagmati |  |  |  | CCC W1: Lead and Coordination Effective leadership and coordination are established and functional | # of cluster coordination conducted at district and palikas | Nos | 4
[7 empty] | # field mission mobilized for need and damage assessment | # of visits | 4
2 | UNICEF | Bagmati |  |  |  | CCC W2. Water Supply Affected populations have safe and equitable access to, and use a sufficient quantity and quality of water to meet their drinking and domestic needs | # of people accessing a sufficient quantity and quality of water for drinking and domestic needs | # of people | 8000
[7 empty] | # of Water quality monitoring conducted in every ward | # of events | 5
3 | UNICEF | Bagmati |  |  |  | CCC W3: Sanitation Affected populations have safe access to, and use appropriate sanitation facilities; and excreta is safely managed | # of people accessing appropriate sanitation services | # of people | 10600
[7 empty] | # of women and girls accessing menstrual hygiene management services | # of people | 2120
4 | UNICEF | Bagmati |  |  |  | CCC W4: WASH in health care facilities and learning environments/schools Affected populations have safe access to, and use, appropriate WASH services in health care and learning facilities/schools for children | # of children using safe and appropriate WASH facilities and hygiene services in learning facilities and safe spaces | # of children | 5 | 2 | Kalika-2 (Gumba )- 2 temporary toilets, 2 handwashing stations, 1,000L HDPE tank & Uttargaya-5 (Nilkantha)- 2 toilets, 2 handwashing stations, 300L tank
5 | UNICEF | Bagmati |  |  |  | CCC W5. Hygiene promotion and community engagement for behaviour and social change At-risk and affected populations have timely access to culturally appropriate, gender- and age-sensitive information, services and interventions related to hygiene promotion, and adopt safe hygiene practices | # people reached with hygiene promotion including hand hygiene sessions (SBC internvention incorporated) | # of people | 10600
[7 empty] | # of community feedback and accountability mechanisms at holding or community centers | # of CFM | 5
[7 empty] | # of people reached with critical WASH supplies (SBC internvention incorporated) | # of people reached | 4250 | 4065 | Uttargaya (47HHs) & Gosaikunda (900 HHs)
Follow data validation
Data to be filled manually
Formulae set